## Sheet1
Third Year Consultancy Group Project ELEC60014
Project | Student Group | Client | Supervisor (based in EEE Dept)
Week 1 - Monday 27 April term begins (you can meet before term starts if you want of course). | Meet with Client for full briefing on project, context and expectations. Write summary of meeting for discussion with IC supervisor. Thursday 29 April students attend two workshops in person in 408 - 11am – 12.30pm Developing Strong Team Dynamics – led by Jess Popplewell, Imperial Career Centre - 2pm – 3.30pm - Running a Successful EEE Consultancy Project – led by Prabhav Reddy, Senior Tutor | Meet with students to brief on project, expectations and any relevant contextual information, available resources etc. | join students in initial meeting with company if possible.
Week 2 | Clarify leaflet with client and supervisor and plan of work, justification of approach and proposed solutions | Sanity check leaflet with students and provide feedback. Arrange site visit | Meet with students to discuss project, explore ideas for approaching project. Check on progress of work and delivery of leaflet.
Week 3 |  |  | provide group with technical support and mentoring if required
Week 4 |  |  | provide group with technical support and mentoring if required
Week 5 | produce draft flyer for supervisor/client (By Friday 29 May 2026) | invited to provide formative feedback on flyer | formative feedback on flyer
Week 6 | Groups submit 2pp A 4 flyer (Friday 5 June 2026)
Week 7
Week 8 | Hackbooth Demonstration and poster presentation (Wednesday 17 June 2026) | Invited to attend hackbooth demonstration and poster presentation, provide feedback on perfomance etc | Attend hackbooth demonstration and poster presentation
Week 9 | submission of documentation and peer assessment (Friday 26 June 2026) |  | Review and mark documentation and provide overall mark for project